## GANNT chart
Housing Magician
| Group-17, ME781 Course Project, IIT-Bombay |  | Project Start: | 2021-10-13
| Housing price predictor app |  | Today: | 2021-10-24
|  |  | Display Week: | 0 |  |  | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22
 | time axis 2021-10-04 to 2021-11-28
Sr.No | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2021-10-04 to 2021-11-28
1 | Problem Definition & Objective
1.1 | Customer (end-user) requirement | Niharika | 100% | 2021-10-14 | 2021-10-23 | 10
1.2 | Market survey (for exisitng solns) | Niharika | 100% | 2021-10-14 | 2021-10-23 | 10
1.3 | Key Differentiator | Niharika | 100% | 2021-10-14 | 2021-10-23 | 10
1.4 | Unique Selling Point (USP) | Niharika | 100% | 2021-10-14 | 2021-10-23 | 10
1.5 | Protection of USP | Niharika | 100% | 2021-10-14 | 2021-10-23
1.6 | Barrier to Market Entry | Niharika | 100% | 2021-10-14 | 2021-10-23
1.7 | Business Case (setup cost and capital) | Niharika | 100% | 2021-10-14 | 2021-10-23 | 10
2 | Technology Lanscape Management
2.1 | Patents | Kaustabh | 100% | 2021-10-14 | 2021-10-23 | 10
2.2 | Published literature | Kaustabh | 100% | 2021-10-14 | 2021-10-23 | 10
2.3 | Open libraries | Kaustabh | 100% | 2021-10-14 | 2021-10-23 | 10
2.4 | Proprietary libraries | Kaustabh | 100% | 2021-10-14 | 2021-10-23 | 10
3 | Project Planning
3.1 | GANNT chart | Lakshya | 100% | 2021-10-14 | 2021-10-23 | 10
3.2 | RASIC chart | Lakshya | 100% | 2021-10-14 | 2021-10-23 | 10
4 | Conceptual Design
4.1 | High level activity object diagrams | Siri Verma | 100% | 2021-10-14 | 2021-10-23 | 10
4.2 | Choice of language, OS, Data set | Siri Verma | 100% | 2021-10-15 | 2021-10-23 | 9
4.3 | ML model selection | Lakshya | 100%
5 | Code Development-1
5.1 | Coding convention practices | Siri Verma | 100% | 2021-10-24 | 2021-10-30 | 7
5.2 | Basic user interface | Siri Verma | 100% | 2021-10-24 | 2021-10-31 | 8
5.3 | Output visualization | Lakshya | 100% | 2021-10-24 | 2021-11-01 | 9
6 | Code Development-2
6.1 | Error handling | Lakshya | 100% | 2021-10-24 | 2021-11-17 | 25
6.2 | Auto document generation | Siri Verma | 100% | 2021-10-24 | 2021-11-18
6.3 | Code testing | Lakshya | 100% | 2021-10-24 | 2021-11-19
7 | Product Marketing
7.1 | Brochure development | Niharika | 100% | 2021-11-20 | 2021-11-25 | 6
7.2 | Marketing presentation | Niharika | 100% | 2021-11-21 | 2021-11-26
7.3 | Marketing Advertisement Video | Lakshya | 100% | 2021-11-23 | 2021-11-24
7.4 | Marketing audio-video of 1min | Siri Verma | 100% | 2021-11-22 | 2021-11-27
8 | Product Demonstration
8.1 | Demonstration presentation | Kaustabh | 100% | 2021-11-21 | 2021-11-27
8.2 | User manual | Lakshya | 100% | 2021-11-22 | 2021-11-28 | 7
Insert new rows ABOVE this one
| SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.