## Group-17 Rasic chart
Housing Magician RASIC Chart (Group-17)
Project Members
|  | Kaustabh | Lakshya | Niharika | Siri Verma
1.1 | Customer (end-user) requirement | A | I | R | I | R | Responsibility
1.2 | Market survey (for exisitng solns) | A | I | R | I | A | Accountable
1.3 | Key Differentiator | A | C | R | I | C | Consulted
1.4 | Unique Selling Point (USP) | I | I | R | A | I | Informed
1.5 | Protection of USP | I | I | R | A
1.6 | Barrier to Market Entry | I | I | R | A
1.7 | Business Case (setup cost and capital) | C | A | R | I
2.1 | Patents | R | I | A | I
2.2 | Published literature | R | I | A | I
2.3 | Open libraries | R | I | A | I
2.4 | Proprietary libraries | R | I | I | I
3.1 | GANNT chart | I | R | A | C
3.2 | RASIC chart | C | R | A | I
4.1 | High level activity object diagrams | A | I | I | R
4.2 | Choice of language, OS, Data set | A | I | C | R
4.3 | ML model selection | C | R | I | A
5.1 | Coding convention practices | I | C | A | R
5.2 | Basic user interface | I | A | I | R
5.3 | Output visualization | I | R | I | A
6.1 | Error handling | I | R | I | A
6.2 | Auto document generation | I | A | I | R
6.3 | Code testing | I | R | A | I
7.1 | Brochure development | A | I | R | I
7.2 | Marketing presentation | I | I | R | A
7.3 | Marketing audio-video of 1min | I | A | I | R
8.1 | Demonstration presentation | R | A | C | I
8.2 | User manual | I | R | I | A
Role
Project Deliverable
(or Activity)